## Task
Sl |  | Action | Contents | Remarks
1 | Files | Need to send Praneeth | Documentation for Range of Parameters (High Limit and Low Limit) for all Subsystems. | Parameter Range Document
2 |  |  | All Subsystems MIB files.
3 |  |  | Documentation for how much Data is Flow in certain time period (5 min)(Data Calculation).
4 | SRS |  | SRS should updated document with all new implementations. | Update Documents
5 | SDD |  | SDD needs to update with the flow of SNMP Request and Response along with bytes size (single request and response for all Subsystems).
6 | LCP | LCP Development | In About Window implement Check sum for all
7 |  |  | Date, DG MIB, UPS MIB, Radio MIB, Switch MIB.
8 |  |  | In configuration window needs to remove EDIT option.
9 |  |  | Needs to implement checksum for all at application level.
10 |  |  | Must be Beep Sound for Traps. | need Verify
11 |  |  | DG,UPS,Radio,Switch Default report should be generate non Trap
12

## WBS Plan
Sl | WBS Item | Description | Status | Start Date | End Date | Deliverables | Remarks
1 | Parameter Range Documentation-Documentation for Range of Parameters (High Limit and Low Limit) for all Subsystems. | Compile and verify High/Low limits for all parameters across subsystems | Done | 2025-08-27 | 2025-08-29 | Parameter Range Document | Delivered to the customer
2 | MIB Collection-MIB files of Syb System. | Collect and verify latest MIB files for all subsystems | Done | 2025-08-27 | 2025-08-27 | Subsystems MIB Package | Delivered to the customer
3 | Period (5 min)(Data Calculation)Documentation | Draft and exemplify 5-min data calculation per subsystem | Done | 2025-08-27 | 2025-09-01 | Data Flow Calculation Doc | Delivered to the customer
4 | SRS Update | Integrate all new features/changes into SRS | Done | 2025-08-27 | 2025-08-27 | Updated SRS Doc | Delivered to the customer
5 | SDD Update- | Document SNMP flows and byte sizes; revise diagrams as needed | Done | 2025-08-27 | 2025-09-06 | Updated SDD Doc | Delivered to the customer
6 | LCP Checksum in About Window | Add checksum logic, document process | Done | 2025-08-27 | 2025-09-01 | Updated LCP, Checksum Tech Note
7 | Date/MIB Versioning | Update docs with date and exact MIB versions | Done | 2025-08-27 | 2025-08-29 | Date & Version Reference Section
8 | Config UI Edit Removal-In the configuration window needs to be removed EDIT option. | Remove Edit button from configuration UI, update guides | Done | 2025-08-27 | 2025-08-29 | implemented in LCP Software
9 | Global Application Checksum | Implement and document application-level checksum | Done | 2025-08-27 | 2025-08-29 | Global Checksum Implementation Note
10 | Trap Beep Notification- | Add/check beep sound for traps, document settings | Done | 2025-08-27 | 2025-08-29
11 | Default Report Generation | Ensure default reporting excludes Traps, document schedule | Done | 2025-08-27 | 2025-08-28 | implemented in LCP Software
12 | STR(Software Test Result) | A summary of test results (pass/fail, completion status) Detailed problem descriptions for failed cases Records of test deviations with rationale and impact assessment | InProgress | 2025-09-13 | 2025-09-21